## Step4Tech
No | Task | Assignee | Assign |  | Actual |  | Progress | Status | Remark
|  |  | Start Date | End Date | Start Date | Start Date
1 | login/logout (function , design) | May Thinzar | 2021-11-08 | 2021-11-09
2 | forget password (function , design) | May Thinzar | 2021-11-10 | 2021-11-11
3 | create profile, update profile (function , design) | May Thinzar | 2021-11-12 | 2021-11-13
4 | show profile (function , design) | May Thinzar | 2021-11-14 | 2021-11-16
5 | show posts list (function , design) | Zaw Win Tin | 2021-11-08 | 2021-11-09
6 | search posts on nav (function , design) | Zaw Win Tin | 2021-11-10 | 2021-11-11
7 | show posts list according to fav categories (function) | Zaw Win Tin | 2021-11-12 | 2021-11-13
8 | show liked posts list (function) | Zaw Win Tin | 2021-11-14 | 2021-11-16
9 | click like btn, count likes (function , design) | May Thin Khaing | 2021-11-16 | 2021-11-17
10 | create feedbacks, show feedbacks , update feedbacks (function , design) | May Thin Khaing | 2021-11-13 | 2021-11-15
11 | post create, post update ,post delete (function , design) | May Thin Khaing | 2021-11-10 | 2021-11-12
12 | show posts list according to fav categories, show liked posts list (design) | May Thin Khaing | 2021-11-08 | 2021-11-09
13 | manage user CRUD (function, design) | Kaung Khant Naing | 2021-11-08 | 2021-11-10
14 | manage post CRUD,manage categories CRUD(function, design) | Kaung Khant Naing | 2021-11-11 | 2021-11-13
15 | statistics -> post popularity chart (function, design) | Kaung Khant Naing | 2021-11-14 | 2021-11-16
17 | statistics -> category popularity chart (function, design) | Kaung Khant Naing | 2021-11-17 | 2021-11-19